## Timeline
Week | Title | Difficulty level | Description | Due Date | Status | Comments
1 | Complete Requirements Document | Medium | Finalize the document and get sign off from instructor | 2025-09-05 | Completed | Get feedback from instructor
2 | Project Planning & Requirements | Medium | Finalize project overview and requirements document. Define detailed user stories for each role (Pet Owner, Veterinarian, Admin). Identify key features for Must Have, Should Have, and Nice to Have categories. Sketch initial wireframes for main screens: Login/Register, Pet Profile, Vet Dashboard, Admin Dashboard. Confirm technology stack and external APIs (Firebase Auth, Firestore, Google Maps API, OpenWeather API). Set up GitHub repository for version control. | 2025-09-12 | In Progress | Get feedback from instructor
3 | Design & Frontend Setup | Medium | Develop Figma prototypes for all key user interfaces. Get prototype approval or feedback from peers/instructor. Create project folder structure for React frontend. Implement basic React app structure: App.js, components/, pages/. Style global CSS and initial layout components (header, footer, navbar). Set up Firebase Authentication and configure user roles (Pet Owner, Veterinarian, Admin). | 2025-09-19
4 | Backend & Database Setup | Medium | Set up Firebase Firestore database. Create collections for users, pets, appointments, medicalRecords. Populate with dummy data for testing. Implement CRUD operations for Pet Owner (Create, Read, Update, Delete pet profiles, track vaccinations, medical history, appointments). Implement CRUD operations for Veterinarian (add/update medical records and care notes). Implement Admin backend functionality (manage user accounts: approve, deactivate, validate). Test database connectivity and basic queries | 2025-09-26 | Not started
5 | Core Feature Implementation | High | Implement Google Maps API integration for Pet Owner to locate nearby vets and pet stores. Implement OpenWeather API integration for weather-based pet care reminders. Build pet appointment booking system. Implement document upload functionality for vaccination certificates and medical records. Begin frontend integration with backend Firestore data. Perform unit testing for CRUD and API functionalities. | 2025-10-03 | Not started
6 | Advanced Features & Testing | High | Implement optional features (Nice to Have): pet milestone tracker (birthdays, weight, achievements), in-app notifications, Veterinarian analytics dashboard. Refine frontend design and responsiveness (desktop and mobile views). Conduct functional testing for all user roles (Pet Owner: login, pet management, appointment booking, reminders; Veterinarian: record updates, recommendations, analytics; Admin: user management, backend monitoring). Fix bugs identified during testing. Document all APIs and feature implementations. | 2025-10-10 | Not started
7 | Deployment & Project Wrap-Up | Medium | Finalize React frontend and ensure full integration with Firebase. Conduct end-to-end testing for all workflows. Deploy the application (React frontend → GitHub Pages; Firestore and Firebase Auth → production-ready). Test deployed version on multiple devices and browsers. Prepare final presentation/demo materials (screenshots, workflow videos, feature descriptions). Submit project and requirements document. | 2025-10-17 | Not started
| Presentation | Easy | Complete project presentation requirements. |  | Not started
Note on B1: SWD: What is the component you are working on?
Note on C1: SWD: What is your perception of how difficult this component will be? Easy ¦ Medium ¦ Difficult
Note on D1: SWD: A brief description of the tasks for this component.
Note on E1: SWD: Your target date for completion
Note on F1: SWD: Not Started In Progress Stalled Completed
Note on G1: SWD: Notes or reminders concerning this component.